## Auto Refree
ID | Risk | Caused by | Effect | Result | Exposure | Priority | Torelance | Mitigaion
1 | Dataset storage privacy | Dependecy on Roboflow software | No record & history | There are chances that we lose the stored data and the history of the game. | 4 | 4 | 16 | Transfering the data to local environment.
2 | Dataset creating Problem | Insufficient Dataset | Object detection Issue | Since the dataset has been made by us, the detection accuracy may not be 100%. | 3 | 4 | 12 | Improving the dataset, collecting more samples.
3 | Camera Communication Problem | Communication Speed on Router | No record | The cameras may not be able to record the game. | 1 | 2 | 2 | Using wired connection
4 | Losing communication between autonoumouce & human refree | Sensor Resolution ,hardware problem | Communication loss, Time Delay | There will be a delay in referee's decision making, if there are any communication issues between autonoum refree and human refree. | 5 | 2 | 10 | It is out of scoop
5 | Defficient View Angle | Adjusment Problem of Cameras | Knowledge efficiency | Miscalculation of the position & distances | 5 | 5 | 25 | Installing more cameras
6 | Environmental Dynamics | Light condistion | Quality of the images | If the light condition of the field is not desired, then the autonoum refree might have issue for detecting the lines an make a decision( detectig the object) | 1 | 1 | 1 | Guarantee desired level of ligting

## Risk Matrix
|  | Low | Med- Low | Med | Med-High | High
probability | 5 | 5 | 10 (ID4) | 15 | 20 | 25 (ID5)
| 4 | 4 | 8 | 12 | 16 ( ID1) | 20
| 3 | 3 | 6 | 9 | 12 (ID2) | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 (ID6) | 2 (ID3) | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
Consequence