## Stakeholder Register
ID | Initials | First Name | Last Name | E-mail | Organization | Sub organisation | Role | Power | Interest
1 | E.H | Rene | Van de Molengraft | m.j.g.v.d.molengraft@tue.nl | TU/e | Tech United | Project Sponsor and Technical Consultant | High | High
2 | A.D | Erjen | Lefeber | a.a.j.lefeber@tue.nl | TU/e |  | Product owner and Human referee | High | High
3 | F.F | Riske | Meijer | r.meijer1@tue.nl | TU/e |  | Program Manager | Low | High
4 | K.A | Tech United team |  |  | TU/e | Tech United | User of the system | Low | High
5 | H.W | Harold | Weffers | h.t.g.weffers@tue.nl | TU/e |  | Program Manager coordinator |  | Low
6 | R.B | Ruben | Beumer | r.m.beumer@tue.nl | TU/e | Tech United | Human Referee(Validation of auto-Ref) | Low | High
7 |  |  |  |  | Robo Cup-MSL |  | User of the system | High | Low
8 |  |  |  |  | TU/e | MSD Trainees | Develop the system | Low | High

## Risk Register
ID | Risk | Domain | How | Severity
1 | Hacking the cameras | Privacy & Security | Our cameras are potentially vulnerable to cyberattacks that can execute a variety of harmful actions that can have impact on the judgment of the refree. | 3
2 | Hacking the refree system | Privacy & Security | Our refree system is potentially vulnerable to cyberattacks that can execute a variety of harmful actions that can have impact on the judgment of the refree. | 3
3 | Data storage privacy | Privacy & Security | There are chances that we lose the stored data and the history of the game. | 3
4 | Blocking camera's vision by an obstacle | Quality & Reliability | If by chance anything blocks the camera's vision, then the refree might miss some imporant details and not being able to make fairfull decision. | 2
5 | Fading out the color of the stickers around the football field | Quality & Reliability | If the labels in the field faded out, then it might be difficult for autonoum refree to detect the lines and make decision. | 3
6 | Camera malfunction | Quality & Reliability | Any functional issues in the camera, can cause a delay in the refree's decision. | 5
7 | Light condition | Quality & Reliability | If the light condition of the field is not desired, then the autonoum refree might have issue for deecting the lines an make a decision. | 3
8 | communication problem between autonoum & human refree | Technical Performance | There will be a delay in refree's decision making, if there are any communication issues between autonoum refree and human refree. | 4
9 | Callibration & tuening of image processing tech | Technical Performance | The accuracy of the current algorithm depends on the method which is used for collibration of the field. | 5
10 | Low confidence on object detection ( detecing between ball,team 1 robot, team 2 robot) | Technical Performance | Since the dataset has been made by us, the detection accuracy may not be accurate.
11 | Lower flexibility of code to different robot players | Technical Performance | If there are any changs in robot's color, our code is not flexible to adjust it in short term. | 8

## Change Register
Change request title | Date submitted | Requested by | Description | Change to schedule | Priority | Approved | Reason
Using Camera instead of TechUnited data | 2023-02-16 | Stakeholders | TechUnited data is not a reliable source of data collection | 2 weeks for defining and changing the scope of the project | High | Yes
Feasibility check for all stationary sensors that we can use | 2023-03-03 | Stakeholders | Erjen wanted to know why we chose the security cameras | 2 days working on feasibility check | Low | Yes
Changing the security cameras with GoPro cameras | 2023-03-09 | Team | The view of the stadium cameras was not good enough | 1 day | Low | No | Didn't provide sufficient view of the field

## Project Schedule Register
| Week | [5 empty] | Final week
Project activities schedule | 1 | 2 | 3 | 4 | 5 | 6 | 7
| 06/02-12/02 | 13/02-19/02 | 20/02-26/02 | 27/02-05/03 | 06/03-12/03 | 13/03-19/03 | 20/03-24/03
Project Management Plan creation | First version | Second version |  |  |  | Final version
2020 MSD project documents review
Hardware and software options evaluation
Project scope definition
New requirements creation
System architecture definition
Software creation
Software integration
Systems test
Real robot soccer match simulation
Documentations and main delivarables | [6 empty] | Final Presentation

## Team Register
ID | Titles | Initials | First Name | Last Name | Degrees | E-mail | Organisation | Position | Role
1 |  | E.H | Elham | Honarvar | M.Sc. | e.honarvar@tue.nl | TU/e | Project Manager+Design Engineer | trainee
2 |  | A.D | Ahmet | Demirel | M.Sc. | a.demirel@tue.nl | TU/e | Architect Engineer+Design Engineer | trainee
3 |  | F.F | Farah | Fadel | M.Sc. | f.fadel@tue.nl | TU/e | Team Leader+Design Engineer | trainee
4 |  | K.A | Atefeh | Dehghannayyeri | M.Sc. | a.dehghannayyeri@tue.nl | TU/e | Quality test Engineer+Design Engineer | trainee

## Deliverable Registration
Documents | Delivery date
Presentation provided for weekly meeting with stakeholders | During each meeting date with stakeholders
Risk Register | 2023-03-16
Stakeholder Register | 2023-02-13
Change Register | Different dates
Team Register | 2023-02-13
System Architecture document | 2023-03-24
Requirement Register | 2023-03-03
Github including all the project files | 2023-03-24
Final Report and powerpoint presentation | 2023-03-24
PMP word document | 2023-03-16
Project Schedule Register | 2023-02-13
Feasibility check document | 2023-03-10

## Requierment Register
General Requirements | Description | Constraints | Description
1 | The AutoRef should be accurate about the decisions it made | 1 | System needs to be mounted on any stadium/competition ground
2 | It should be reliable, can work in different stadiums and independent of area of gameplay and time of the game | 2 | System needs to maintain a connection with Refbox and a competition PC
3 | A final delivery suitable to the team's resources should be decided | 3 | System needs to be adaptable to rule/procedure changes
4 | Personal goals of the team members should be achieved during the process | 4 | System needs to be able to permit data retrieval after the match
5 | A validation method should be presented and used
6 | The system should have logs of the match and can show evidence of violations when needed
7 | Proper documentation should be provided
8 | The project should build on the work of the previous years
9 | The system can communicate with the human referee, have feedback, and assist during the match
10 | The project should allow the next generation to work on top of this year's results.
Behavioral Requirements
1 | System needs to be able to check game start/stop procedures and able to send signal (via Refbox.)
2 | System needs to set and get time of the match and eventually start/stop the match.
3 | System needs to monitor the match, acquire related data, and deduce relevant information.
4 | System needs to judge positions during the play and decide award/punishment situations.
5 | System needs to be able to log the game. The data can be used as evidence, so that the format should be proper or convertible.
Functional Requirements
1 | AutoRef shall be aware of the time and use this information to start and stop the match.
2 | AutoRef shall comply with MSL Rulebook while deciding violations and following procedures
3 | AutoRef shall decide an award or punishment regarding the violations and procedures during the match
4 | AutoRef shall gather data and can comprehend its reliability
5 | AutoRef can estimate game states by using data gathered during the match
6 | The game states can be listed as follows: The positions and velocities of soccer robots for each delta-T Ball engagement of each robot Robot and team id Robot’s pose – angular orientation Positions of the lines and specific areas in the field. The field line position the ball has touched last before leaving the play area. The time elapsed between the first and last touch of the robot during dribbling. The position and velocity of the ball. Time
Performance Requirements
1 | All hardware regarding the AutoRef shall be compatible with MSL organization environment
2 | AutoRef shall give permission to users to modify pre-defined game rule parameters and/or deploy some/all the rules
3 | AutoRef shall be connected to Refbox via TBD with maximum TBD latency
4 | AutoRef shall be capable of sending/receiving digital ON/OFF signals to/from AutoRef.
5 | AutoRef shall record/store game data as well as log history.
6 | AutoRef shall allow users to use stored data and download it.
7 | AutoRef shall upload game data automatically a TBD deposit and ensure its safety during the process.
8 | AutoRef shall create a virtual coordinate system that overlaps with field lines originating from corner spot.
9 | AutoRef shall acquire data in each TBD second and estimate game states max TBD cm for positions and TBD cm/s for velocities relative to the field line coordinate system.
10 | AutoRef shall decide a violation within TBD seconds.